EFWA EXCELLENCE HUB     Level 3 · Leadership

Continuous Improvement Playbook

Run a disciplined pipeline of waste-reduction projects using PDCA

New to this? Start here Continuous improvement means making many small, sustained gains rather than one big fix. The method is PDCA - Plan, Do, Check, Act - a simple four-step cycle for testing and locking in improvements. This playbook shows you how to keep a backlog of ideas and run each through PDCA.

What PDCA means

| Step | What you do |
| --- | --- |
| Plan | Define the problem, root cause, target and owner. |
| Do | Trial the change on a small scale. |
| Check | Measure the result against the target. |
| Act | If it worked, standardise it. If not, adjust and re-run. |

1. Keep a backlog of ideas

Capture every waste-reduction idea in one list. Prioritise high value + low effort first.

| Improvement idea | Est. value | Effort | Priority |
| --- | --- | --- | --- |

2. Run each project through PDCA

Plan [ problem, root cause, target, owner ]

Do [ trial the change, small scale ]

Check [ measure vs target ]

Act [ standardise the gain, or adjust and repeat ]

Worked example — one PDCA cycle Plan: prep trim waste high; root cause = inconsistent method; target −20%; owner = shift lead. Do: trial a photo standard on one line for two weeks. Check: trim waste down 28% - beat the target. Act: roll the standard to all lines; add to induction training so it sticks.

3. Hold the gain

- Write every successful improvement into standard work.

- Add a monthly control check so it doesn’t slip back.

- Feed the biggest remaining losses (from the Loss Map, L3.05) back into the backlog.

The discipline that matters most Finish projects before starting new ones. A pipeline of ten half-done ideas saves nothing; three completed and standardised saves real money.

Using this document Yellow highlighted [ CLIENT TO COMPLETE ] fields are for you to fill in with your own information. Everything else is ready to use as-is.